## SADARA Project Plan
SADARA ES-Portal Migration / Upgrade
| PROJECT TITLE |  | START DATE
| SADARA ES-Portal Migration / Upgrade |  | 2023-01-02 |  |  | PROJECT DURATION
| PROJECT MANAGER |  | End Date |  |  | in days
| Reda Sherif |  | 2023-04-20 |  |  | 109
WBS NO. | TASK NAME | STATUS | ASSIGNED TO | START DATE | END DATE | DURATION in days | COMMENTS | STATUS
1 | Project Preparation | Complete |  | 2022-12-20 | 2023-01-02 | 14 |  | Not Started
1.1 | – Detailed Project Work Plan/ Resources, including key milestones | Complete |  | 2022-12-20 | 2022-12-25 |  |  | In Progress
1.2 | – Resources onboarding and release process | Complete |  | 2022-12-25 | 2022-12-26 |  |  | Complete
1.3 | – Knowledge transfer plan | Complete |  | 2022-12-26 | 2022-12-27 |  |  | On Hold
1.4 | – Project Plan | Complete |  | 2022-12-27 | 2022-12-28
1.5 | – Communication and reporting plan | Complete |  | 2022-12-28 | 2022-12-29
1.6 | – Project Kick Off | Complete |  | 2022-12-29 | 2022-12-30
1.7 | – Project Initiation | Complete |  | 2022-12-30 | 2022-12-31
2 | PROJECT Business Blueprint (LLD - HLD) |  |  | 2023-01-02 | 2023-01-20 | 19
2.1 | – Technical Architecture Design (including To-Be landscape) | In Progress |  | 2023-01-02 | 2023-01-05
2.2 | – Network design and firewall mapping | In Progress |  | 2023-01-05 | 2023-01-08
2.3 | – Solution approach | In Progress |  | 2023-01-08 | 2023-01-10
2.4 | – Integration and Migration approach | In Progress |  | 2023-01-10 | 2023-01-11
2.4 | – Delta modification adjustment approach | In Progress |  | 2023-01-11 | 2023-01-12
2.4 | – Installation/restore, upgrade and Configurations approach | In Progress |  | 2023-01-11 | 2023-01-11
2.4 | – Rollback plan | In Progress |  | 2023-01-11 | 2023-01-18
2.4 | – Modify existing Functional and Technical Design Documents to reflect the new changes. | Not Started |  | 2018-01-18 | 2023-01-19
3 | PROJECT Realization |  |  | 2023-01-21 | 2023-02-28 | 39
3.1 | – Installation, Configuration, and Integration Guide |  |  | 2023-01-21 | 2023-02-05
3.2 | – Test Charter and Plan (checklist) |  |  | 2023-02-05 | 2023-02-14
3.3 | – Finalize All environments Migration and upgrade |  |  | 2023-02-14 | 2023-02-28
4 | Testing and Final Preparation |  |  | 2023-02-28 | 2023-03-28 | 29
4.1 | – Conduct System Integration Test |  |  | 2023-02-28 | 2023-03-03
4.2 | – VA Test |  |  | 2023-03-03 | 2023-03-12
4.3 | – Conduct User Acceptance Test |  |  | 2023-03-12 | 2023-03-17
4.4 | – User Acceptant Sing-Off |  |  | 2023-03-17 | 2023-03-23
4.5 | – Defects Logs |  |  | 2023-03-23 | 2023-03-25
4.6 | – Conduct knowledge transfer. |  |  | 2023-03-25 | 2023-03-26
4.7 | – Unit Test results |  |  | 2023-03-27 | 2023-03-27
4.8 | – Cutover plan |  |  | 2023-03-27 | 2023-03-27
4.9 | – Go Live Plan |  |  | 2023-03-28 | 2023-03-28
5 | Go Live & Support |  |  | 2023-03-28 | 2023-04-20 | 24
5.1 | – Production Deployment |  |  | 2023-04-05 | 2023-04-10
5.2 | – Conduct hyper-care and daily monitoring of issues/alerts of system |  |  | 2023-04-10 | 2023-04-15
5.3 | – Validation of Go-Live activities |  |  | 2023-04-15 | 2023-04-18
5.4 | – Lessons learned |  |  | 2023-04-16 | 2023-04-19
5.5 | – Close Issues List |  |  | 2023-04-10 | 2023-04-20